## Instructions
Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2215-swen-261-06-c-5guys
Testing Team Name | fill in when doing cross-team testing
TESTING NOTES:
- Login to the site as an administrator (username = admin) in order to test deleting adding and updating monkeys.
- Pre-existing users to test are userJ1 and adrian
- To run project run "mvn compile exec:java" within estore-api and "ng serve --open" within estore-ui/angular-monkey-estore

## Empty Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a buyer I want to see a list of products so that I choose what to purchase. | Given that I am on the e-store site when I am not on the Products page then I must see a means to navigate to the Products page.
Given that I am not on the Products page when I choose the Products page then I am taken to the Products page.
Given that I am on the Products page when there are no products in the inventory I see a message indicating that that there are no products available.
Given that I am on the products page when there are products in the inventory then I see each product and short description.
Given that I am on the products page when there are products in the inventory then I see a means to add each product to my shopping cart.
As an owner/buyer I want the monkeys to have an id, Name, Price, Species and Description, rented | Given I am attempting to create a monkey When I am a Owner than it should include an id, Name, Price, Species and Description
Given I am attempting to update a monkey When I am an Owner than it should include an id, Name, Price, Species and Description
Given I am attempting to delete a monkey When I am an Owner than it should delete an id, name price, species, and description
Given I am attempting to get all monkeys When I am an Owner or Buyer than I should see all the ids, Names, Prices, Species and Descriptions
Given I am attempting to search for a monkey When I am a Buyer than it should display a list of monkeys each with an id, Name, Price, Species and Description
Given I create a monkey its value for rented should be set to false by default
As a user I want a login screen so that I can easily login to my account. | GIVEN the need for a user interface WHEN I plan to log in to my profile THEN I expect a login page to be present and usable.
GIVEN I submit my user name WHEN I try to log in THEN I expect to be logged into my profile.
GIVEN I input a username WHEN that username exists in the file system THEN the system should check whether the username belongs to an Owner or Buyer and send them to the inventory or the product list respectively.
GIVEN I input a username to login WHEN That username doesn't exist in the file system THEN the system should not grant access to the rest of the site
GIVEN the user wants to create a new Buyer user WHEN they are entering a username THEN the system should create a new Buyer user with the entered username.
GIVEN the user wants to create a new Buyer user WHEN the entered username is taken THEN then the system should not grant access to the rest of the site
As a buyer I want to be able to search for a monkey by name | GIVEN I enter a name into the search bar WHEN I press the search button THEN I expect that the list of monkeys should display any monkeys that were searched for
As an owner I want the ability to easily edit the details of products listed on the website as well as add or delete items. | Given I am logged in as an owner when I access the owner page then I will see a list of all the products that I can edit.
Given I am logged in as an owner when I access the owner page then I will be able to delete products.
Given I am logged in as an owner when I access the owner page then I will have an add monkey option that allows me to design a new product listing.
As a user I want a product page so that I can easily view the details of products listed on the website as well as add to cart. | GIVEN I select a monkey WHEN I am viewing the buyer product list THEN I want to see its specific details regarding its species, price, and description
GIVEN I select the 'add to cart' button WHEN I am viewing a monkey's product page, THEN I expect that monkey to be in my cart
As a customer I want a shopping cart page so that I can easily view and delete items in my cart. | GIVEN I am logged in and have items in my cart WHEN I access this page THEN I expect to see every item in my shopping cart
GIVEN I am logged in and have items in my cart WHEN I remove an item from my shopping cart THEN I expect the product to be added back to inventory and removed from my cart
As a Buyer I want to access a list that contains every product I can purchase so I can move them to my shopping cart. | GIVEN I enter a login WHEN my username belongs to a Buyer THEN a list of items in the inventory available for purchase should be shown.
GIVEN a product's availability changes WHEN I am viewing the list THEN the availability should be updated on this page accordingly
GIVEN I click on a product WHEN I am viewing the list THEN a product page should open
As a user I want a create account screen so that I can easily make an account on the website and use it in the future. | GIVEN the need for a user interface WHEN I try to create an account THEN I expect a create account page to be present and usable.
GIVEN I want a user interface WHEN creating a profile THEN I expect there will be a user interface to easily create an account.
As a customer I want to be able to have my cart saved in between sessions so that I do not have to re add items to my cart. | GIVEN that I want the items in my shopping cart to be saved WHEN I have not yet purchased the items THEN I expect the items that I placed in my cart to still be there, even after logging out
As an owner, I want the website to look professional and stylish so that it is presentable to viewers who may be potential customers. | Given I am active on the e-store when I view the website then I expect it to look professional and stylish
As a customer, I want to see a page that displays the monkeys I am currently renting so that I can return monkeys and write reviews for them. | GIVEN someone is on their rental page WHEN the return button is clicked THEN the monkey's rented status should update to not rented and the monkey should be removed from the page.
As a customer I want to checkout so that I can purchase my products. | GIVEN I request to checkout WHEN I have a shopping cart with one or more products inside, THEN the system should remove the product(s) from the e-store's inventory and return a list of product objects that were purchased.
GIVEN I request to checkout WHEN I have an empty shopping cart, THEN the system should return an error explaining that you cannot checkout without products.
As a customer I want to be able to write reviews so that I can share my experience with a certain product with other users. | GIVEN that I have purchased a product WHEN I attempt to post a review THEN I expect the review to be posted on the product page.
As a customer I want to be able to read reviews so that I can read why users rated products as they did. | Given that I am on a products page when I scroll to the review section then I expect to see product reviews.
As a customer I want to see a products average rating so that I know what people thought about the product. | Given that I am looking at the product listing when the product is on screen then I expect to see the average rating of the product.
Given that the product has a listing page when the product receives a new review then the review score should be added to the current average.

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a buyer I want to see a list of products so that I choose what to purchase. | Given that I am on the e-store site when I am not on the Products page then I must see a means to navigate to the Products page. | Pass | AB; 3/14/22 | Pass | AB; 3/31/22
| Given that I am not on the Products page when I choose the Products page then I am taken to the Products page. | Pass | AB; 3/14/22 | Pass | AB; 3/31/22
| Given that I am on the Products page when there are no products in the inventory I see a message indicating that that there are no products available. | Fail | AB; 3/14/22; The buyer product list does not display a message indicating that there are no products available until you leave the page and come back to it | Pass | TW; 3/28/22
| Given that I am on the products page when there are products in the inventory then I see each product and short description. | Pass | AB; 3/14/22 | Pass | AB; 3/31/22
| Given that I am on the products page when there are products in the inventory then I see a means to add each product to my shopping cart. | Pass | AB; 3/14/22 | Pass | AB; 3/31/22
As an owner/buyer I want the monkeys to have an id, Name, Price, Species and Description, rented | Given I am attempting to create a monkey When I am a Owner than it should include an id, Name, Price, Species and Description | Pass | JY; 3/14/22; The POST request to create a user includes them all, though the default is null for species, and description | Pass | AB; 3/31/22
| Given I am attempting to update a monkey When I am an Owner than it should include an id, Name, Price, Species and Description | Pass | JY; 3/14/22 | Pass | AB; 3/31/22
| Given I am attempting to delete a monkey When I am an Owner than it should delete an id, name price, species, and description | Pass | JY; 3/14/22 | Pass | AB; 3/31/22
| Given I am attempting to get all monkeys When I am an Owner or Buyer than I should see all the ids, Names, Prices, Species and Descriptions | Pass | JY; 3/14/22 | Pass | AB; 3/31/22
| Given I am attempting to search for a monkey When I am a Buyer than it should display a list of monkeys each with an id, Name, Price, Species and Description | Pass | JY; 3/14/22 | Pass | AB; 3/31/22
| Given I create a monkey its value for rented should be set to false by default | Pass | JY; 3/14/22, Rented is not a displayed value currently, though it can be seen as monkeys with rented true are unavailable to be added to cart for Buyer Users | Pass | AB; 3/31/22
As a user I want a login screen so that I can easily login to my account. | GIVEN the need for a user interface WHEN I plan to log in to my profile THEN I expect a login page to be present and usable. | Pass | JH; 3/14/2022 | Pass | AB; 3/31/22
| GIVEN I submit my user name WHEN I try to log in THEN I expect to be logged into my profile. | Pass | JH; 3/14/2022 | Pass | AB; 3/31/22
| GIVEN I input a username WHEN that username exists in the file system THEN the system should check whether the username belongs to an Owner or Buyer and send them to the inventory or the product list respectively. | Pass | JH; 3/14/2022 | Pass | AB; 3/31/22
| GIVEN I input a username to login WHEN That username doesn't exist in the file system THEN the system should not grant access to the rest of the site | Pass | JH; 3/14/2022 | Pass | AB; 3/31/22
| GIVEN the user wants to create a new Buyer user WHEN they are entering a username THEN the system should create a new Buyer user with the entered username. | Pass | JH; 3/14/2022 | Pass | AB; 3/31/22
| GIVEN the user wants to create a new Buyer user WHEN the entered username is taken THEN then the system should not grant access to the rest of the site | Pass | JH; 3/14/2022 | Pass | AB; 3/31/22
As a buyer I want to be able to search for a monkey by name | GIVEN I enter a name into the search bar WHEN I press the search button THEN I expect that the list of monkeys should display any monkeys that were searched for | Pass | AB; 3/14/22 | Pass | AB; 3/31/22
As an owner I want the ability to easily edit the details of products listed on the website as well as add or delete items. | Given I am logged in as an owner when I access the owner page then I will see a list of all the products that I can edit. | Pass | AB; 3/14/22 | Pass | AB; 3/31/22
| Given I am logged in as an owner when I access the owner page then I will be able to delete products. | Pass | AB; 3/14/22 | Pass | AB; 3/31/22
| Given I am logged in as an owner when I access the owner page then I will have an add monkey option that allows me to design a new product listing. | Pass | AB; 3/14/22 | Pass | AB; 3/31/22
As a user I want a product page so that I can easily view the details of products listed on the website as well as add to cart. | GIVEN I select a monkey WHEN I am viewing the buyer product list THEN I want to see its specific details regarding its species, price, and description | Pass | AB; 3/14/22 | Pass | AB; 3/31/22
| GIVEN I select the 'add to cart' button WHEN I am viewing a monkey's product page, THEN I expect that monkey to be in my cart | Pass | AB; 3/14/22 | Pass | AB; 3/31/22
As a customer I want a shopping cart page so that I can easily view and delete items in my cart. | GIVEN I am logged in and have items in my cart WHEN I access this page THEN I expect to see every item in my shopping cart | Pass | AB; 3/14/22 | Pass | AB; 3/31/22
| GIVEN I am logged in and have items in my cart WHEN I remove an item from my shopping cart THEN I expect the product to be added back to inventory and removed from my cart | Pass | AB; 3/14/22 | Pass | AB; 3/31/22
As a Buyer I want to access a list that contains every product I can purchase so I can move them to my shopping cart. | GIVEN I enter a login WHEN my username belongs to a Buyer THEN a list of items in the inventory available for purchase should be shown. | Pass | AB; 3/14/22 | Pass | AB; 3/31/22
| GIVEN a product's availability changes WHEN I am viewing the list THEN the availability should be updated on this page accordingly | Fail | AB; 3/14/22; The rented status does not properly reflect on the buyer product list until you leave and return to the page | Pass | TW; 3/28/22
| GIVEN I click on a product WHEN I am viewing the list THEN a product page should open | Pass | AB; 3/14/22 | Pass | AB; 3/31/22
As a user I want a create account screen so that I can easily make an account on the website and use it in the future. | GIVEN the need for a user interface WHEN I try to create an account THEN I expect a create account page to be present and usable. | Pass | JH; 3/14/2022 | Pass | AB; 3/31/22
| GIVEN I want a user interface WHEN creating a profile THEN I expect there will be a user interface to easily create an account. | Pass | AB; 3/14/22 | Pass | AB; 3/31/22
As a customer I want to be able to have my cart saved in between sessions so that I do not have to re add items to my cart. | GIVEN that I want the items in my shopping cart to be saved WHEN I have not yet purchased the items THEN I expect the items that I placed in my cart to still be there, even after logging out | Pass | AB; 3/14/22 | Pass | AB; 3/31/22
As an owner, I want the website to look professional and stylish so that it is presentable to viewers who may be potential customers. | Given I am active on the e-store when I view the website then I expect it to look professional and stylish |  | CURRENTLY UNIMPLEMENTED | Pass | AB; 3/31/22
As a customer, I want to see a page that displays the monkeys I am currently renting so that I can return monkeys and write reviews for them. | GIVEN someone is on their rental page WHEN the return button is clicked THEN the monkey's rented status should update to not rented and the monkey should be removed from the page. |  | CURRENTLY UNIMPLEMENTED | Pass | AB; 3/31/22
As a customer I want to checkout so that I can purchase my products. | GIVEN I request to checkout WHEN I have a shopping cart with one or more products inside, THEN the system should remove the product(s) from the e-store's inventory and return a list of product objects that were purchased. |  | CURRENTLY UNIMPLEMENTED | Pass | AB; 3/31/22
| GIVEN I request to checkout WHEN I have an empty shopping cart, THEN the system should return an error explaining that you cannot checkout without products. |  | CURRENTLY UNIMPLEMENTED | Fail | AB; 3/31/22; There is currently no message explaining that you cannot checkout without products
As a customer I want to be able to write reviews so that I can share my experience with a certain product with other users. | GIVEN that I have purchased a product WHEN I attempt to post a review THEN I expect the review to be posted on the product page. |  | CURRENTLY UNIMPLEMENTED | Pass | AB; 3/31/22
As a customer I want to be able to read reviews so that I can read why users rated products as they did. | Given that I am on a products page when I scroll to the review section then I expect to see product reviews. |  | CURRENTLY UNIMPLEMENTED | Pass | AB; 3/31/22
As a customer I want to see a products average rating so that I know what people thought about the product. | Given that I am looking at the product listing when the product is on screen then I expect to see the average rating of the product. |  | CURRENTLY UNIMPLEMENTED | Pass | AB; 3/31/22
| Given that the product has a listing page when the product receives a new review then the review score should be added to the current average. |  | CURRENTLY UNIMPLEMENTED | Pass | AB; 3/31/22